## Testcases
|  |  |  | Date | 2022-11-03
|  |  |  | Team ID | PNT2022TMID13127
|  |  |  | Project Name | Inventory Management System for Retailers
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Commnets | TC for Automation(Y/N) | BUG ID | Executed By
LoginPage_TC_OO1 | Functional | Home Page | Verify user is able to see the Login/Register popup when user clicked on Submit button |  | 1.Enter the URL and click on Register/Login tab 2.Give the required credentials 3. Message pops up on the top | http://169.51.207.234:30399/ | Login/Signup popup should display | Working as expected | Pass
LoginPage_TC_OO2 | UI | Login Page | Verify the UI elements in Login Page |  | 1. Enter URL and click on Login tab 2. Check whether the following UI components are shown a.username textbox b.password textbox c.submit button d.If account doesn't exist Redirect to register page using the hyperlink | http://169.51.207.234:30399/ | Application should show below UI elements: a.username textbox b.password textbox c.submit button d.hyperlink works | Working as expected | Pass
LoginPage_TC_OO3 | Functional | Home page | Verify user is able to log out of the application |  | 1. Login to the application 2. Click on the logout option 3. Message pops up on the top | Username: jeevanantham@gmail.com password: jeeva26 | User should navigate back to homepage | Working as expected | pass
LoginPage_TC_OO4 | Functional | Home page | Verify user is able to switch among multiple tabs |  | 1. Enter URL and login to the application 2. Click on products, location and product movement tab | Username: jeevanantham@gmail.com password: jeeva26 | Redirect to the respective page | Working as expected | pass
LoginPage_TC_OO4 | Functional | product movements | Verify whether the datas are updated properly |  | 1. Enter URL and login to the application 2. Switch to product movements page 3. Click on add product movements button 4. Enter approprite details and click on add button | Username: jeevanantham@gmail.com password: jeeva26 From Location: Chennai To Location: Kochi Product ID: Product-1 Quantity: 50 | 1.update added on product movement tab with a pop up message 2. Update reflected on dashboard after fetching data from database | Data not fetched properly | Fail | need to verify |  | bug- 7895 | Jhanani J

## Testscearnios
Test Scenarios
Login/Logout
1 | Verify user is able to see login page
2 | Verify whether the password is hidden
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to get a pop up message
5 | Verify login page elements
Add Location
1 | Verify user is able to add location
2 | Verify user is able to edit the location
3 | Verify user is able to delete the location
4 | Verify user is able to see the update in the dashboard
5 | Verify user is able to see the entry in products movement page
Add Products
1 | Verify user is able to add products in product page
2 | Verify user is able to edit the product
3 | Verify user is able to delete the product
4 | Verify user is able to edit the cost and quantity
5 | Verify user is able to see the product in products movement page
Add Products Movement
1 | Verify user is able to add product movements
2 | Verify user is able to edit the product Movement
3 | Verify user is able to delete the product Movement
4 | Verify user is able to see the quantity change in the locations after adding the movement
5 | Verify user is able to see the product movement change in dashboard